## Plan_Of_Work
S.No. | Task | Planned duration (in weeks) | Name of Deliverables
1 | Research and feasibility check | 1 | Research
2 | Gathering the raw images | 1 | Data Gathering
3 | Setup a cloud platform with storage, compute and software | 1 | Cloud setup
4 | Implement PII data masking | 5 | Application
5 | Implement texture analysis using a computer vision algorithm | 5 | Application
6 | Build visualization showing efficacy of products | 3 | Reporting

## Project_Plan
Skin texture change detection for clinical trials | 2020-09-06 | 2020-09-13 | 2020-09-20 | 2020-09-27 | 2020-10-04 | 2020-10-11 | 2020-10-18 | 2020-10-25 | 2020-11-01 | 2020-11-08 | 2020-11-15 | 2020-11-22 | 2020-11-29 | 2020-12-06 | 2020-12-13 | 2020-12-20
| W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16
Research and feasibility check | bar: 2020-09-06 to 2020-09-13
Gathering the raw images | bar: 2020-09-13 to 2020-09-20
Setup a cloud platform with storage, compute and software | bar: 2020-09-20 to 2020-09-27
Implement PII data masking | bar: 2020-09-27 to 2020-11-01
Implement texture analysis using a computer vision algorithm | bar: 2020-10-25 to 2020-11-29
Build visualization showing efficacy of products | bar: 2020-11-29 to 2020-12-20